## Sheet1
| Project Start Date: |  | 2022-10-10 |  |  | Status:
[6 empty] | Completed |  | Ongoing |  | Pending |  | High risk
Gantt Chart
Milestone Description | Category | Assigned To | Progress | Start | Week# | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Sprint # 2 – Project Planning | Completed | aalawy3 | 100% | 2022-10-10 | Week8 | bar: Week 8
Prepare and test the lo-cal environment (JDK, Node, NPM, Postgres, .. etc.) | Completed | aalawy3 | 100% | 2022-10-17 | Week9 | bar: Week 9
Create and test Heroku applications/repositories (Java backend applica-tion, Angular frontend application, Postgres DB, Heroku repositories, … etc.) | Completed | aalawy3 | 100% | 2022-10-24 | Week10 | bar: Week 10
Implement Firebase authentication service from Google. | Ongoing | aalawy3 | 10% | 2022-10-31 | Week11 | bar: Week 11
Create the required classes and bind to the DB tables (Patient, Observation, Medication, Appointment, User, … etc.) | Pending | aalawy3 | 0% | 2022-11-07 | Week12 | bar: Week 12
Create the APIs services (inpuBloodPressure(), getAverageBloodPres-sure(), getNextAp-pointment(), get-NextMedication(), … etc.) | Pending | aalawy3 | 0% | 2022-11-14 | Week13 | bar: Week 13
Create and test the landpage/dashboard layhout using Angular | Pending | aalawy3 | 0 | 2022-11-21 | Week14 | bar: Week 14
Create and test other screens (input blood pressure, display all doctor visits, re-view/update medica-tions, … etc.) | Pending | aalawy3 | 0 | 2022-11-28 | Week15 | bar: Week 15
Deploy the application to Heroku | Pending | aalawy3 | 0 | 2022-11-28 | Week15 | bar: Week 15