## Sheet1
Legend:
| Project Start Date: |  | 2022-10-10 |  |  |  |  | On Track |  |  |  | Low Risk |  |  |  | Med Risk |  |  |  | High Risk
Gantt Chart
[6 empty] | October | [21 empty] | November | [29 empty] | December
[6 empty] | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
[6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
Milestone Description | Category | Assigned To | Progress | Start | Week# | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Sprint # 2 – Project Planning | On Track | aalawy3 | 100% | 2022-10-10 | Week8 | bar: Week 8 M to Week 8 S
Prepare and test the lo-cal environment (JDK, Node, NPM, Postgres, .. etc.) | Low Risk | aalawy3 | 70% | 2022-10-17 | Week9 | bar: Week 9 M to Week 9 S
Create and test Heroku applications/repositories (Java backend applica-tion, Angular frontend application, Postgres DB, Heroku repositories, … etc.) | On Track | aalawy3 | 0% | 2022-10-24 | Week10 | bar: Week 10 M to Week 10 S
Implement Firebase au-thentication service from Google. | On Track | aalawy3 | 0% | 2022-10-31 | Week11 | bar: Week 11 M to Week 11 S
Create the required clas-ses and bind to the DB tables (Patient, Observa-tion, Medication, Ap-pointment, User, … etc.) | On Track | aalawy3 | 0% | 2022-11-07 | Week12 | bar: Week 12 M to Week 12 S
Create the APIs services (inpuBloodPressure(), getAverageBloodPres-sure(), getNextAp-pointment(), get-NextMedication(), … etc.) | On Track | aalawy3 | 0% | 2022-11-14 | Week13 | bar: Week 13 M to Week 13 S
Create and test the landpage/dashboard layhout using Angular | On Track | aalawy3 | 0% | 2022-11-21 | Week14 | bar: Week 14 M to Week 14 S
Create and test other screens (input blood pressure, display all doctor visits, re-view/update medica-tions, … etc.) | On Track | aalawy3 | 0% | 2022-11-28 | Week15 | bar: Week 15 M to Week 15 S
Deploy the application to Heroku | On Track | aalawy3 | 0% | 2022-11-28 | Week15 | bar: Week 15 M to Week 15 S